## Slide 1: Budget Planning

## Slide 2: Budget Management
Importance
Estimating costs to compare and select
Methods of Estimating
Managing the Budget
  Budget timeline
  Budget variances

## Slide 3: Importance of budget planning
Cost is one of the three project constraints
A budget is a plan or forecast
Cost management also includes tracking and managing variances from the planned expenditures
Detailed estimates are important

## Slide 4: Estimating costs to compare and select projects
Payback, rate of return or NPV (or combine them)
Need accurate numbers but must balance with the cost of getting more accurate estimates

## Slide 5: Estimating methods
Analogous estimate
  Find a similar project or task and assume this one will be the same or similar
  The more experience the estimator has, the better this works
  Learn from each project
  DPCI (Darnell-Preston Complexity Index) can help with benchmarking
Parametric estimate
  Parameters such as number of square feet for a building; number of kitchens, bathrooms, etc. for a house.
Bottom-up estimating
  Estimate each item or task and add them together
  Generally more accurate but takes more effort to create

## Slide 6: Estimating Guidelines
Don’t gold-plate: estimate what you expect, and meet that estimate.

## Slide 7: Managing the Budget
Cash flow
  Make a plan of WHEN the outflows will occur, and ensure that the money is available on time
  Contingency reserves
    For unexpected expenses that arise during the project
    There are almost always some surprises, but can’t predict at the start what it will be
    Project Manager does not allocate to the sub-projects but manages it centrally
    Can be spent and still be within the original project budget
  Management Reserves
    For scope changes
    Not likely to be spent; not part of project baseline

## Slide 8: Reporting Progress: Earned value management
Budgeted Cost of work Scheduled | BCWS | Detailed estimates for each activity in the project
Planned Value | PV | Total budgeted cost as of a certain date in the project
Earned Value | EV | Budgeted cost of the completed work as of a certain date in the project
Actual Cost | AC | Actual cost of the completed work as of a certain date in the project
Budget at Completion | BAC | Total budgeted costs for the entire project

## Slide 9: Project Cost Chart
Chart: 
| February | March | April | May | June | July
Budget Baseline | 10000 | 12000 | 22000 | 30000 | 40000 | 45000
BAC

## Slide 10: Budget Baseline and Project Cost Chart
The project budget is usually shown graphically, illustrating the cumulative planned spending.
Typical shape for the budget curve is s-shaped, with less spending at the beginning and end of the project.
Add the periodic expenditures on a regular basis to create the Project Cost Chart.

## Slide 11: Project Cost Chart (up to May)
Chart: 
| February | March | April | May | June | July
Actual Expenditures | 5000 | 7000 | 30000 | 35000
Budget Baseline | 10000 | 12000 | 22000 | 30000 | 40000 | 45000
BAC
AC

## Slide 12: Schedule Variance: SV
Difference between planned and actual progress
SV=EV-PV
Positive value: project is ahead of schedule
Zero: project is on-time
Negative: project is behind schedule

## Slide 13: Cost Variance: CV
The difference between the earned value and the actual cost is the cost variance:
CV=EV-AC
If positive, you are achieving more than you predicted for the money
If zero, you are right on the plan
If negative, you are achieving less than you predicted for the money

## Slide 14: Schedule Performance Index: SPI
Compares progress on the scope to spending:
SPI = EV/PV
SPI less than one indicates the project is behind schedule
SPI of one is right on schedule
SPI greater than one the project is ahead of schedule

## Slide 15: Cost Performance Index: CPI
Compares the budget spent to date with progress to date:
CPI=EV/AC
A value greater than one: under budget
Equal to one: on budget
Less than one: overspending the budget

## Slide 16: Estimated Cost to Complete the Project: ETC
Formula to use depends on what the PM expects with regard to future project costs and whether the original budget assumptions remain valid

## Slide 17: ETC if past variances are not expected to continue:
ETC = BAC – EV

## Slide 18: ETC if past variances are expected to continue at the same level
ETC = (BAC – EV)/CPI

## Slide 19: Estimated Final Project Cost: EAC
EAC = ETC + AC

## Slide 20: Budget Timeline
Contractual agreements often require partial payments
Prepare a schedule, based on contractual and other expenditure requirements

## Slide 21: Budget Management Summary
Cost estimations may be used to choose between options
Managing the budget includes
  Estimating costs and setting a budget
  Determining when the budgeted costs should occur
  Tracking expenditures
  Managing variances between the budget and the expenditures
Methods of Estimating
  Analogous, Parametric, Bottom-up
Managing the Budget
  Budget timeline
  Budget variances

## Slide 22: Budget Management Summary (continued)
Budgeting and Cost Management are important activities for project managers
There are several methods for estimating the costs
Estimated costs may be used to choose between options
Project progress and budget management are closely related and can be managed with indices: BCWS, PV, SV, AC, CV, SPI, CPI, ETC, BAC and EAC
Contingency funds allow for the unexpected
Reporting to the team and to management are important components in budget management

## Slide 23: Questions?