## Slide 1: Risk Management Planning

## Slide 2: Project Risk Management
Definition and Importance
Four ways to handle risks
Risk Management Processes
  Plan Risk Management
  Identify Risks
  Evaluate Risks
  Plan Risk Responses
Project Risk by Phases

## Slide 3: Project Risk Definition
Project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives such as scope, schedule, cost and quality
A risk may have
  one or more causes
  one or more impacts
Source: PMBOK 5th Edition.

## Slide 4: Project risk
More than the sum of the identified risks—there’s an overarching risk as well

## Slide 5: What can be done about risks?
Avoid
  Use another method
  Don’t perform the risky activity
Transfer
  Share or transfer the impact
  Insurance is a major approach used here
Mitigate
  Reduce probability of an impact
  Reduce degree of potential impact
Accept
  The activity is necessary and you cannot think of any cost-effective ways to mitigate the potential impacts of the risk

## Slide 6: Example
Before paint can be applied, the surface must be cleaned. Toxic chemicals are one method of cleaning. Risk: someone may injure their skin or their eyes due to a spill or splash of the chemical. Options:
  Avoid:
    find another method of cleaning—would high-pressure water work as well? Could a longer delay for curing be considered? Is painting really necessary?
  Transfer:
    get insurance on the workers; if toxic exposure is based on time limits, use a larger workforce for shorter each. (An unethical method sometimes used: outsource internationally)
  Reduce the probability of injury:
    require protective equipment such as clothing and safety goggles and mask; provide training and information to the workers.
  Reduce the degree or impact of possible injury:
    ensure that onsite first aid attendants are available; eyewash stations, etc.
  Accept: do nothing

## Slide 7: More definitions
Risk Appetite
  Degree of uncertainty an entity is willing to take on in anticipation of a reward
Risk tolerance
  The degree, amount, or volume of risk that an organization or individual with will withstand
Risk threshold
  Point above which a stakeholder or organization is no longer willing to accept the level of uncertainty or impact

## Slide 8: Example
Think about Northern Gateway, a proposed oil pipeline in northern British Columbia
  Risk appetite may be greater for the stakeholders who anticipate personal gain, or who value economic benefits more highly
  Risk tolerance and threshold may be very low for those concerned about impact on wildlife, particularly if they do not see the value of the anticipated benefits in economic activity.
On a personal level
  Is there any level of uncertainty you will accept for your child’s safety?
Note that there are also risks for “do nothing”

## Slide 9: Plan Risk Management (process)
Make an overall plan of how the project will identify, track an respond to risks
Inputs:
  Project plan, project charter, shareholder register, enterprise environmental factors, organizational process assets
Tools:
  Analytical techniques
  Expert judgment
  Meetings
Outputs
  Risk Management Plan
  (note that this becomes input to the other four risk management processes: Identify Risks, Perform Qualitative Risk Analysis, Perform Quantitative Risk Analysis, Plan Risk Responses)
Comment:
  The complexity of the Risk Management Plan will vary with the complexity of the overall project.

## Slide 10: Identify Risks (process)
Inputs
  Most of the other documents you already have regarding the project
  Enterprise environmental factors and Organizational Process Assets
Tools and Techniques
  Fact finding: Documentation reviews, etc.
  Risk Breakdown Structure
  Diagramming techniques
  SWOT
  Expert judgment
Outputs
  Risk Register

## Slide 11: Risk Breakdown Structure
Groups and categorizes risks
Identifies Response (Mitigation)

## Slide 12: Risk Breakdown Structure Example

## Slide 13: Risk Register
List of identified Risks
List of potential Responses
Over the life of the project will add:
  Updates to probabilities of the risk occurring
  Information on occurrences, if any
  Information on actual responses and the success or lack of success of those responses

## Slide 14: Qualitative Risk Analysis
Should always be done
Considers what are the risks, what can be done about them
Categorization of risks
Urgency of risks
  May vary through the project:
    Most concern for imminent risks
    at some point a risk may no longer be an issue
Updates the risk register:
  New information about risk probability and impacts
  New rankings or scores
  New assumptions

## Slide 15: Probability and Impact Matrix
Chart: Impact
| Category 1 | Category 2 | Category 3 | Category 4
Series 1
Series 2
Series 3 | 90

## Slide 16: Probability and Impact Matrix
Place identified risks on the matrix
The closer to top-right, more important to try to identify how to move down and/or to the left.

## Slide 17: Quantitative Risk Analysis
Quantitative Risk Analysis attempts to use published data to quantify the risks:
  Industry data about probabilities
  Data about typical costs
Uses a variety of tools
  Data gathering
  Sensitivity Analysis
  Expected monetary value analysis
  Modeling and simulation
  Expert judgment
May be expensive; usually is cost-justified for large, complex projects
May NOT be cost-justified on smaller projects
Would also update the risk register with the new information

## Slide 18: In-class activity
Consider a major proposed project locally, the replacement of the Patullo Bridge
With your group, identify at least ten things that could happen to impact the success of a bridge replacement project. Place each of the ten items on your Probability and Impact Matrix
On another colour of post-it, identify things that could be done about the risk. Draw an arrow toward “reduced probability” or “reduced impact” or both
Be ready to explain to the instructor or to members of another group, and at that point, if your explanation is accepted, you may MOVE your risk to the left or DOWN
Get a group member to take a photo of your matrix to post to the class website

## Slide 19: Controlling Risks
Throughout the project, the project manager must continue to update the risk register, as new risks are identified, and the project retires consideration of risks that are no longer possible
Risk reassessments and risk audits can be used to monitor and control the risk management processes
There are costs associated with the contingency reserve, so if it can be identified that some portion of this reserve can be released, it is a benefit to the organization and to the project

## Slide 20: Project Change Management
Identification of a risk or occurrence of a risk may create a need for a Project Change.
Change Management is part of the Project Integration Management knowledge group
Reminder of a typical change management process:
  Identify a change request
  Consider the impacts and costs (may have a committee for this)
  Make a decision
  Identify what plans must be updated
  Inform affected stakeholders of the decision
  Proceed
The PMO may have forms and template procedures available for project use

## Slide 21: Risk throughout the project
The levels of risk change throughout the project
The risk-over-time profile may be typical to certain project types:
  Early for projects that use new technology
  Late for politically sensitive projects
  During procurement where this is a large portion of the budget

## Slide 22: Risk Management - Summary
Project risk is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives such as scope, schedule, cost and quality
A risk may have
  one or more causes
  one or more impacts
…continued on next slide

## Slide 23: Risk Management – Summary (continued)
Risk Management Processes
  Plan Risk Management
  Identify Risks
  Perform Qualitative Risk Analysis
  Perform Quantitative Risk Analysis
  Plan Risk Responses
  Control Risks

## Slide 24: Project Risk Management (PMBOK 5)
Risk Management Process in the Planning Process Group
  Plan Risk Management
  Identify Risks
  Perform Qualitative Risk Analysis
  Perform Quantitative Risk Analysis
  Plan Risk Responses
Risk Management Processes in the Monitoring and Controlling Process Group
  Control Risks

## Slide 25: Questions?